## WVD_CAF_Project_ TaskList
Id | Work Item Type | Title
501 | Epic | Strategy/Plan
502 | Feature | Assess the Digital landscape of current infrastructure
503 | User story | Identify and document contacts for this project
504 | User story | Present Windows Virtual Desktop: Prerequisites and requirements
505 | Task | Review supported Operating Systems and licensing requirements
506 | Task | Confirm Operating Systems to deploy
507 | Task | Confirm licensing requirements have been met
508 | Task | Review Azure Active Directory requirements
509 | Task | Align assets to cloud offerings to calculate pricing
510 | User story | Review and document in-scope Users and their Application requirements
511 | Task | Review Microsoft applications requirements like Office apps
512 | Task | Review requirements for third party commercial applications
513 | Task | Review requirements for custom applications like customer business apps
514 | Task | Confirm in-scope application(s) that require GPU acceleration
515 | User story | Review and confirm OS images to deploy
516 | Task | Review the marketplace images like predefined Azure Gallery OS Images
517 | Task | Review the custom OS images requirements
518 | User story | Review and document Windows Virtual Desktop session hosts and host pool requirements
519 | User story | Present FS Logix: Prerequisites and requirements
520 | User story | Present SMB File Share: Prerequisites and requirements
521 | User story | Extend to Azure vs Connect to on-premises
522 | Epic | Ready - Landing zone
523 | Feature | Configure Azure landing zone for Azure Tenant
524 | User story | Provision an Azure tenant and set up Azure Active Directory
525 | User story | Provision the required Administrator roles in Azure AD
526 | User story | Set up the Windows Virtual Desktop tenant
527 | Feature | Configure Azure landing zone for Domain (Hybrid)
528 | User story | Integrate Azure AD with Active Directory Domain Services
529 | User story | Network configuration for WVD
530 | Task | Azure Bastion Configuration to access azure virtual machine
531 | Task | Configure Azure Virtual Network
532 | Task | Configure Azure VPN Gateway (Site-to-Site VPN)
533 | Task | Configure S2S VPN between Azure and on-premises network / firewall
534 | User story | Resilient Identity Pattern (RIP)
535 | Task | Extend on-premises AD Forest to Azure
536 | Task | Create 2x Domain Controllers in Azure (one in each geo redundant datacenter region)
537 | Task | Add to on-premise Forest
538 | Feature | Configure Azure landing zone for Domain (Greenfield)
539 | User story | Configure Azure AD Domain Services
540 | User story | Network configuration for WVD
541 | Task | Azure Bastion Configuration to access azure virtual machine
542 | Feature | Windows 10 Image Customization and Deployment
543 | User story | Create custom images with business line apps
544 | Task | Create a custom image in Azure
545 | Task | Validate custom images
546 | Epic | Adopt - Windows Virtual Desktop
547 | Feature | Deploy Windows Virtual Desktop in Microsoft Azure
548 | User story | Configure Windows Virtual Desktop host pool
549 | User story | Provision a Windows Virtual Desktop host pool
550 | User story | Configure apps and desktops for users
551 | User story | Configure FS Logix container to store user profiles
552 | Task | Validate pre-requirements FS logix container have been completed
553 | Task | Deploy and Configure FS Logix container
554 | User story | Migrate RDS Workloads to WVD
555 | Task | Migration to Personal/Pooled Desktops
556 | Task | Migrate existing user profiles to FS Logix Profile Containers
557 | Epic | Govern - Windows Virtual Desktop
558 | Feature | Configure Azure governance policies for WVD
559 | User story | Azure Security Center Policies
560 | Task | Create and manage policies
561 | Epic | Manage - Windows Virtual Desktop
562 | Feature | Optimize Windows Virtual Desktop in Microsoft Azure
563 | User Story | Automate depth and breadth scaling for Windows Virtual Desktop host pools
564 | User Story | Migrate files from local file shares into Azure storage using Azure File Sync
565 | User Story | Configure OneDrive in Office 365 in Windows Virtual Desktop host pools
566 | User Story | Separate user profiles from virtual machines with FS Logix profiles
567 | User story | Backup & Recovery (BUR)
568 | Task | Configure Azure Backup